## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: Online Stationary Store | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE: Ms. Shafaque Syed | [6 empty] | DATE | [6 empty] | 2022-04-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
Week 1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Siddhant Darekar Lakshit Patil, Shreyash Ghute, Kail Khan | 2022-01-26 | 2022-01-29 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
Week 2 | Identifying the functionalities of the Mini Project | Siddhant Darekar Lakshit Patil, Shreyash Ghute, Kail Khan | 2022-02-05 | 2022-02-10 | 2 | 100% | bar: WEEK 3 M to WEEK 5 F
Week 3 | Discussing the project topic with the help of paper prototype. | Siddhant Darekar Lakshit Patil, Shreyash Ghute, Kail Khan | 2022-02-15 | 2022-02-20 | 2 | 100% | bar: WEEK 5 M to WEEK 6 F
Week 4 | Presentation I | Siddhant Darekar Lakshit Patil, Shreyash Ghute, Kail Khan | 2022-03-16 | 2022-03-16 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
2 | Project Design and Implementation
Week 5 | Designing Graphical User Interface | Siddhant Darekar, Lakshit Patil | 2022-02-05 | 2022-03-05 | 1 | 100% | bar: WEEK 10 M to WEEK 10 F
Week 6 | Database Design | Siddhant Darekar | 2022-03-08 | 2022-03-18 | 1 | 100% | bar: WEEK 10 M to WEEK 10 F
Week 7 | Database Connectivity of all modules | Siddhant Darekar | 2022-03-20 | 2022-03-30 | 1 | 100% | bar: WEEK 11 M to WEEK 12 F
Week 8 | Integration of all modules and Report Writing | Siddhant Darekar,Shreyash Ghute, Lakshit Patil, Kaif Khan | 2022-04-01 | 2022-04-08 | 1 | 100%
Week 9 | Presentation II | Siddhant Darekar,Shreyash Ghute, Lakshit Patil, Kaif Khan | 2022-04-10 | 2022-04-10 | 2 | 100% | bar: WEEK 12 M to WEEK 14 F