## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
Weather Prediction System | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
Prof. Manjusha Shelke | [6 empty] | DATE | [6 empty] | 2022-03-25
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Rohan Ahire | 2022-01-17 | 2022-01-28 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F; WEEK 5 M to WEEK 5 F
1.2 | Identifying the functionalities of the Mini Project | Chirag Kadam | 2022-01-31 | 2022-02-11 | 2 | 100% | bar: WEEK 3 M to WEEK 5 F
1.3 | Discussing the project topic with the help of paper prototype. | Rohan Ahire, Chirag Kadam, Pratham Bhagwat, Atharva Ankalwar | 2022-02-14 | 2022-02-25 | 2 | 100% | bar: WEEK 5 M to WEEK 6 F
1.4 | Designing the Graphical User Interface(GUI) | Rohan Ahire | 2022-02-28 | 2022-03-11 | 2 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 7 M to WEEK 8 F
1.5 | Presentation I | Rohan Ahire, Chirag Kadam, Pratham Bhagwat, Atharva Ankalwar | 2022-03-14 | 2022-03-18 | 1 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 9 M to WEEK 9 F
2 | Project Design and Implementation
2.1 | Integration of all modules and Report Writing | Rohan Ahire, Chirag Kadam | 2022-04-04 | 2022-04-08 | 1 | 100% | bar: WEEK 5 M to WEEK 5 F
2.2 | Presentation II | Rohan Ahire, Chirag Kadam, Pratham Bhagwat, Atharva Ankalwar | 2022-04-11 | 2022-04-19 | 2 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 12 M to WEEK 14 F